## Dress up Items _20200711
PRE-DRESS UP HEAVY EQUIPMENT LIST | [13 empty] | L&P drawing still to be released
LSPC PJT
S.NO | TAG | SERVICE | OVERALL DIMENSIONS |  | WEIGHT | [5 empty] | Platforms and Ladders | [5 empty] | Piping |  |  | E&I |  | INSTALLATION SCHEDULE | Remarks
|  |  | DIAMETER | HEIGHT | FAB & SHIP WEIGHT (Ton) | PF & LD (Tons) | EXT. PIPING (Tons) | INSULATION (Tons) | tons | ETA | Vendor | Ident code | ROS DRW Date | ROS Material Date | ETA updated 18-Jun-2020 | Delta | ROS ISO DRW | ROS Piping Support DRW | Material
|  |  | (mm) | (mm) | (A) | (B) | (C) | (D)
1 | 10-T-2000 | QUENCH OIL TOWER | 9600 | 26800 | 340.7 | 57.8 | 6.0 (only pipe supports) | 34 | 440 | 2020-11-30 | POSCO | C3NYDVYF | #REF! | #REF! | 2020-09-12 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-01-26 | 1,600 Ton
2 | 10-T-2100 | QUENCH WATER TOWER | 9300 | 31750 | 515.6 | 57.3 | 9.0 (only pipe supports) | 14.9 | 598 | 2020-12-19 | POSCO | C3NYDVYU | #REF! | #REF! | 2020-09-12 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-01-27 | 1,600 Ton
3 | 10-T-2300 | CAUSTIC TOWER | 4600 | 46500 | 274.9 | 37.2 | 2.5 (only pipe support) | 16.7 | 332.3 | 2020-12-26 | POSCO | C3NYDVY9 | #REF! | #REF! | 2020-09-12 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-02-24 | 1,600 Ton
4 | 10-T-2440 | HP DEPROPANIZER | 4250 | 36500 | 154.9 | 27.9 | 2.1 (only pipe support) | 11.4 | 197.3 | 2020-12-26 | POSCO | C3NYDVYL | #REF! | #REF! | 2020-09-12 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-03-04 | 600 Ton
5 | 10-T-2450 | LP DEPROPANIZER | 2850 | 45900 | 108.1 | 20.5 | 2.2 (only pipe support) | 8.7 | 140.5 | 2021-01-15 | POSCO | C3NYDVYM | #REF! | #REF! | 2020-09-24 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-01-27 | 1,600 Ton
6 | 10-T-2510 | DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM | 2300 | 47900 | 454.4 | 37.1 | 6.0 (only pipe support) | 27.8 | 526.3 | 2020-12-19 | POSCO | C3NYDVYN | #REF! | #REF! | 2020-10-20 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-03-19 | 1,600 Ton
7 | 10-T-2540 | DEMETHANIZER & DEMETHANIZER REFLUX DRUM | 2700 | 50850 | 321.3 | 31.2 | 6.0 (only pipe support) | 37.1 | 396.6 | 2020-12-26 | POSCO | C3NYDVYP | #REF! | #REF! | 2020-11-08 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-03-21 | 1,600 Ton
8 | 10-T-2570 | DEETHANIZER | 4300 | 48300 | 246.1 | 29.1 | 4.5 (only pipe support) | 14.7 | 295.4 | 2021-01-25 | POSCO | C3NYDVYR | #REF! | #REF! | 2020-11-08 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-03-18 | 1,600 Ton
9 | 10-T-2580 | C2 TOWER | 4400 | 70600 | 292.3 | 35.3 | 40 | 53.2 | 420.8 | 2020-12-26 | POSCO | C3NYDVYS | #REF! | #REF! | 2020-09-24 | #REF! | 2020-11-15 | #REF! | n/a | See MTO | See MTO | 2021-03-16 | 1,600 Ton
10 | 10-T-2630 | SECONDARY DEETHANIZER | 2700 | 26550 | 70.5 |  |  |  | 91.65 | 2020-11-19 | POSCO | C3NYDVYX | #REF! | #REF! | 2020-10-15 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2021-01-04 | 600 Ton
11 | 10-T-2640 | C3 TOWER | 6400 | 83500 | 654.8 | 44.7 | 56.8 | 37.8 | 794.1 | 2020-12-04 | POSCO | C3NYDVZ3 | #REF! | #REF! | 2020-10-15 | #REF! | 2020-11-15 | #REF! | n/a | See MTO | See MTO | 2021-03-15 | 1,600 Ton
12 | 10-T-2710 | DEPENTANIZER | 2400 | 37450 | 58 | 10.3 |  | 11 | 79.3 | 2020-10-30 | POSCO | C3NYDVYE | #REF! | #REF! | 2020-10-15 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-12-29 | 600 Ton
13 | 10-T-3000 | PREDISTILLATION TOWER | 2000 | 38300 | 49 | 16.64 |  | 8.126 | 73.766 | 2020-09-18 | ATAD STEEL | C3467N2U | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-11-17 | 600 Ton
14 | 10-T-3020 | MAIN WASHER | 2000 4500 | 3100 55550 | 140.3 | 18.348 |  | 18.687 | 177.335 | 2020-09-18 | ATAD STEEL | C3467N2F | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-11-19 | 600 Ton
15 | 10-T-3030 | AFTER WASHER | 1900 | 52000 | 135.8 | 19.046 |  | 10.515 | 165.361 | 2020-10-19 | ATAD STEEL | C3467N1D | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-11-21 | 600 Ton
16 | 10-T-3040 | RECTIFIER | 3100 3800 | 3700 23000 | 154.6 | 26 |  | 15 | 195.6 | 2020-10-19 | ATAD STEEL | C3467N1E | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-12-18 | 600 Ton
17 | 10-T-3050 | DEGASSER | 2800 | 44000 | 111.8 | 23.602 |  | 26.887 | 162.289 | 2020-10-19 | ATAD STEEL | C3467N1F | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-12-20 | 600 Ton
18 | 10-T-3080 | BUTADIENE TOWER | 2100 | 38250 | 58.2 | 16.33 |  | 8.545 | 83.075 | 2020-09-18 | ATAD STEEL | C3467N1H | #REF! | #REF! | 2020-09-03 | #REF! | n/a | #REF! | n/a | n/a | n/a | 2020-12-22 | 600 Ton
======Clarification of weight calculation======
1. Weight allowance.
Acc.to below sentence in 3.6 and 3.8, we are supposed to increase weight with certain allowance.
Dressed equipment : 20% allowance
Undressed equipment : 10% allowance
In “PRE DRESSUP ITEM” of attached BOQ, above 20% allowance also needs to be applied to Listed 17 items?
All items except for above 17 items needs to apply 10% allowance?
è20191002 TPSK Reply :
Article 3.6 – Applicable. The fabrication weight has not yet been fixed, it could be subject to minor variations. Therefore, bidder shall consider additional 10% for all equipment total weight including pre-dressed up equipment also. For example C3 tower total weight be considered as 917 ton (=834 ton X 110%).
Article 3.8 – Not applicable. The SUBCONTRACTOR already received the list of pre-dressed equipment and relevant weight.
2. Weighing operation
I would like to clarify weighing operation with certificates before installation is required.
Reason why we ask is that weighing operation before installation will extend schedule significantly.
Normally the fabrication yard will weigh the equipment before shipping the cargo, maybe this can be utilized to certify equipment weight except for dress up items.
è20191002 TPSK Reply :
Article 3.7 of Detail Scope of work : Applicable. The supply of cell Load is SUBCONTRACTOR scope work and shall be considered in Its total cost without cost form modification.
Regarding each weight, Shall be reviewd by engineering

## DALs (hidden)
DAL for T-2580 | DAL for T-2640
2DAE00-HV-25087-01 | 2DAE00-C3R-26065-01
2DAE00-HL-25096-01 | 2DAE00-C3R-26201-01
2DAE00-HV-25163-01 | 2DAE00-HM-26066-01
2DAE00-HL-25086-01 | 2DAE00-VT-26257-01
2DAE00-HM-25089-01 | 2DAE00-LS1-26183-01
2DAE00-HL-25088-01 | 2DAE00-PA-26184-01
2DAE00-VT-25947-01 | 2DAE00-LN-26185-01
2DAE00-LS1-25210-01
2DAE00-PA-25211-01
2DAE00-LN-25212-01

## Electrical components 10-T-2580 (hidden)
10-T-2580 | C2 TOWER |  |  | 10-T-2640 | C3 TOWER
ITEM | DESCRIPTION | UNIT | QUANTITY | ITEM | DESCRIPTION | UNIT | QUANTITY
A | Power |  |  | A | Power
A1 | 150mm Cable Ladder c/w Cover & Accessories | meter | 85 | A1 | 150mm Cable Ladder c/w Cover & Accessories | meter | 100
B | Lighting & Acessories |  |  | B | Lighting & Acessories
B1 | 2x36W Fluorescent Light Stanchion Mount (Ex-Type) | Nos. | 14 | B1 | 2x36W Fluorescent Light Stanchion Mount (Ex-Type) | Nos. | 9
B2 | 60W LED Linear Light Stanchion Mount (Ex-Type) | Nos. | 20 | B2 | 60W LED Linear Light Stanchion Mount (Ex-Type) | Nos. | 20
B3 | 31W LED Linear Light Stanchion Mount (Ex-Type) | Nos. | 16 | B3 | 31W LED Linear Light Stanchion Mount (Ex-Type) | Nos. | 20
B4 | Lighting Junction Box (Ex-Type) | Nos. | 50 | B4 | Lighting Junction Box (Ex-Type) | Nos. | 49
B5 | 2C+G 25mm2 Lighting Cable | meter | 80 | B5 | 2C+G 25mm2 Lighting Cable | meter | 100
B6 | 2C+G 16mm2 Lighting Cable | meter | 180 | B6 | 2C+G 16mm2 Lighting Cable | meter | 200
B7 | 2C+G 2.5mm2 Lighting Cable | meter | 250 | B7 | 2C+G 2.5mm2 Lighting Cable | meter | 250
B8 | 25mm Dia. HDG Conduit | meter | 100 | B8 | 25mm Dia. HDG Conduit | meter | 100
B9 | 50mm Dia. HDG Conduit | meter | 50 | B9 | 50mm Dia. HDG Conduit | meter | 50
C | Receptacle & Acessories |  |  | C | Receptacle & Acessories
C1 | 16A 1 Ph. Receptacle (Ex-Type) | Nos. | 8 | C1 | 16A 1 Ph. Receptacle (Ex-Type) | Nos. | 7
C2 | Receptacle Junction Box (Ex-Type) | Nos. | 8 | C2 | Receptacle Junction Box (Ex-Type) | Nos. | 7
D | Aircraft Warning Light |  |  | D | Aircraft Warning Light
D1 | NIL |  |  | D1 | Aircraft Warning Light | Lot | 1
E | Lightning Protection |  |  | E | Lightning Protection
E1 | 600mm High Air Terminal | Nos. | 2 | E1 | 600mm High Air Terminal | Nos. | 2
E2 | 3000mm High HDG Pole | Nos. | 2 | E2 | 3000mm High HDG Pole | Nos. | 2
E3 | 70mm2 Bare Copper Earthing Cable | meter | 170 | E3 | 70mm2 Bare Copper Earthing Cable | meter | 200
E4 | Earthing Cable Clips | Nos. | 170 | E4 | Earthing Cable Clips | Nos. | 200

## Instrument material (hidden)
ITEM | TAG | SERVICE | WBS | HEIGHT (mm) | 150mm Cable Ladder GI (meter) | 100mm tube tray SS (meter)
1 | 10-T-2580 | C2 TOWER | 2D | 70600 | 85 | 40
2 | 10-T-2640 | C3 TOWER | 2D | 83500 | 100 | 50
3 | 10-T-2000 | QUENCH OIL TOWER | 2A | 26800 | 32 | 32
4 | 10-T-2100 | QUENCH WATER TOWER | 2A | 31750 | 38 | 20
5 | 10-T-2300 | CAUSTIC TOWER | 2E | 46500 | 56 | 25
6 | 10-T-2440 | HP DEPROPANIZER | 2E | 36500 | 44 | 20
7 | 10-T-2450 | LP DEPROPANIZER | 2B | 45900 | 55 | 25
8 | 10-T-2510 | DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM | 2D | 47900 | 58 | 30
9 | 10-T-2540 | DEMETHANIZER & DEMETHANIZER REFLUX DRUM | 2D | 50850 | 61 | 30
10 | 10-T-2570 | DEETHANIZER | 2D | 48300 | 58 | 30
11 | 10-T-2660 | DEBUTANIZER | 2C | 24900 | 30 | 15
12 | 10-T-2710 | DEPENTANIZER | 2C | 39400 | 47 | 25
13 | 10-T-2720 | RERUN TOWER | 2C | 29000 | 35 | 20
14 | 10-T-3000 | PREDISTILLATION TOWER | 3A | 38300 | 46 | 25
15 | 10-T-3050 | DEGASSER | 3A | 43750 | 53 | 25
16 | 10-T-3080 | BUTADIENE TOWER | 3A | 38250 | 46 | 25
17 | 10-T-3020 | MAIN WASHER | 3A | 60050 | 72 | 35
18 | 10-T-3030 | AFTER WASHER | 3A | 52500 | 63 | 30
20 | 10-T-3040 | RECTIFIER | 3A | 60900 | 73 | 35

## Dress up Items (hidden)
PRE-DRESS UP HEAVY EQUIPMENT LIST
REV.G
LSPC PJT
S.NO | TAG | SERVICE | WBS | BLOCK | OVERALL DIMENSIONS |  | REVISED WEIGHT - 04 July 2019 |  |  |  |  | DRESS UP TYPE | DRESS UP AREA | HEAVY EQUIPMENT PRELIMINARY INSTALLATION SCHEDULE
[5 empty] | DIAMETER | HEIGHT | FAB & SHIP WEIGHT (Ton) | PF & LD (Tons) | EXT. PIPING (Tons) | INSULATION (Tons) | TOTAL (Tons)
[5 empty] | (mm) | (mm) | (A) | (B) | (C) | (D) | (E=A+B+C+D) |  |  | START | FINISH
1 | 10-T-2000 | QUENCH OIL TOWER | 2A | #B | 9600 | 26800 | #REF! | 90 |  | 37 | #REF! | Partial dress up | NEAR FOUNDATION | #REF! | #REF!
2 | 10-T-2100 | QUENCH WATER TOWER | 2A | #B | 9300 | 31750 | #REF! | 91 |  | 16.5 | #REF! | Partial dress up | NEAR FOUNDATION | #REF! | #REF!
3 | 10-T-2300 | CAUSTIC TOWER | 2E | #A | 4600 | 46500 | #REF! | 27 |  | 15.6 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
4 | 10-T-2440 | HP DEPROPANIZER | 2E | #A | 4250 | 36500 | #REF! | 26.4 |  | 11.6 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
5 | 10-T-2450 | LP DEPROPANIZER | 2B | #B | 2850 | 45900 | #REF! | 20.5 |  | 8.1 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
6 | 10-T-2510 | DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM | 2D | #A | 2300 | 47900 | #REF! | 31 |  | 31.8 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
7 | 10-T-2540 | DEMETHANIZER & DEMETHANIZER REFLUX DRUM | 2D | #A | 2700 | 50850 | #REF! | 28 |  | 41.2 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
8 | 10-T-2570 | DEETHANIZER | 2D | #A | 4300 | 48300 | #REF! | 49 |  | 26 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
9 | 10-T-2580 | C2 TOWER | 2D | #A | 4400 | 70600 | #REF! | 59 | 40 | 58.2 | #REF! | Full Dress up | NEAR FOUNDATION | #REF! | #REF!
10 | 10-T-2630 | SECONDARY DEETHANIZER | 2B | #B | 2700 | 26550 | 70.5 |  |  |  | 91.65 | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
11 | 10-T-2640 | C3 TOWER | 2D | #A | 6400 | 83500 | #REF! | 75 | 56.8 | 39.2 | #REF! | Full Dress up | NEAR FOUNDATION | #REF! | #REF!
12 | 10-T-2710 | DEPENTANIZER | 2C | #B | 2400 | 37450 | #REF! | 15.4 |  | 6.2 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
13 | 10-T-3000 | PREDISTILLATION TOWER | 3A | #B | 2000 | 38300 | #REF! | 16.64 |  | 8.126 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
14 | 10-T-3020 | MAIN WASHER | 3A | #B | 2000 4500 | 3100 55550 | #REF! | 18.348 |  | 18.687 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
15 | 10-T-3030 | AFTER WASHER | 3A | #B | 1900 | 52000 | #REF! | 19.046 |  | 10.515 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
16 | 10-T-3040 | RECTIFIER | 3A | #B | 3100 3800 | 3700 23000 | #REF! | 26 |  | 15 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
17 | 10-T-3050 | DEGASSER | 3A | #B | 2800 | 44000 | #REF! | 23.602 |  | 26.887 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
18 | 10-T-3080 | BUTADIENE TOWER | 3A | #B | 2100 | 38250 | #REF! | 16.33 |  | 8.545 | #REF! | Partial dress up | NO NEAR FOUNDATION | #REF! | #REF!
======Clarification of weight calculation======
1. Weight allowance.
Acc.to below sentence in 3.6 and 3.8, we are supposed to increase weight with certain allowance.
Dressed equipment : 20% allowance
Undressed equipment : 10% allowance
In “PRE DRESSUP ITEM” of attached BOQ, above 20% allowance also needs to be applied to Listed 17 items?
All items except for above 17 items needs to apply 10% allowance?
è20191002 TPSK Reply :
Article 3.6 – Applicable. The fabrication weight has not yet been fixed, it could be subject to minor variations. Therefore, bidder shall consider additional 10% for all equipment total weight including pre-dressed up equipment also. For example C3 tower total weight be considered as 917 ton (=834 ton X 110%).
Article 3.8 – Not applicable. The SUBCONTRACTOR already received the list of pre-dressed equipment and relevant weight.
2. Weighing operation
I would like to clarify weighing operation with certificates before installation is required.
Reason why we ask is that weighing operation before installation will extend schedule significantly.
Normally the fabrication yard will weigh the equipment before shipping the cargo, maybe this can be utilized to certify equipment weight except for dress up items.
è20191002 TPSK Reply :
Article 3.7 of Detail Scope of work : Applicable. The supply of cell Load is SUBCONTRACTOR scope work and shall be considered in Its total cost without cost form modification.